## Team
Initials | First | Last | Email | GitHub Username
SR | Sanjeev | Rajasekaran | sanjeev95@rocketmail.com | sanz94
VB | Vikas | Bhat | vikasbhat7793@gmail.com | vikasb7
ON | Ogadinma | Njoku | ogadinman2001@yahoo.com | ogadinman2001
XP | Xiaopeng | Yuan | 397551318@qq.com | smallv0221
GitHub Repository: https://github.com/sanz94/SSW-555
Story ID | Story Name | Story Description | Owner | Estimated Size | Effort Required(in minutes) | Status
US01 | Correct gender for role | Husband should be a male and Wife should be a female | VB | 120 | 130 | Need to be implemented
US02 | Divorce before death | Divorce can only occur before death | SR | 90 | 100 | Need to be implemented
US03 | Male last names | The last name of all male members should be same | ON | 110 | 150 | Need to be implemented
US04 | List living single | List all people who are above 30 and alive yet not married. | ON | 140 | 180 | Need to be implemented
US05 | Less then 150 years old | Age shouldn't be above 150 | VB | 80 | 100 | Need to be implemented
US06 | Marriage after 14 | No one should be married before 14 | SR | 90 | 105 | Need to be implemented
US07 | Siblings should not marry | siblings shouldn't marry each other | SR | 100 | 120 | Need to be implemented
US08 | Unique IDs | All individual and family ids should be unique | VB | 90 | 110 | Need to be implemented
US09 | Fewer than 15 siblings | Maximum 15 siblings in a family | ON | 80 | 120 | Need to be implemented
US10 | Marriage Before Death | Check if Marriage date is before Death date | SR | 30 | 80
US11 | Unique First name Families | Check if all first names in families are unique | SR | 30 | 80
US12 | Marriage before Divorced | Marriage date of an indivdual should occur before divorce date | VB | 30 | 80
US13 | Birth before marriage | Birth date of an individual should occur before marriage date | VB | 30 | 80
US14 | Sibling Spacing | Birth dates of siblings should be more than 8 months apart or less than 2 days apart (twins may be born one day apart, e.g. 11:59 PM and 12:02 AM the following calendar day) | XP | 30 | 80
US15 | Multiple births <= 5 | No more than five siblings should be born at the same time | XP | 30 | 80
US16 | List living married |  | ON | 30 | 80
US17 | Dates before current date |  | ON | 30 | 80
US18 | No marriages to descendants | Parents should not marry any of their descendants | SR
US19 | Siblings should not marry | Siblings should not marry one another | SR
US20 | First cousins should not marry | First cousins should not marry one another | XP
US21 | Aunts and uncles | Aunts and uncles should not marry their nieces or nephews | XP
US22 | Correct gender for role | Husband in family should be male and wife in family should be female | VB
US23 | Unique IDs | All individual IDs should be unique and all family IDs should be unique | VB
US24 | Unique name and birth date | No more than one individual with the same name and birth date should appear in a GEDCOM file | ON
US25 | Unique families by spouses | No more than one family with the same spouses by name and the same marriage date should appear in a GEDCOM file | ON

## Backlog
Sprint | Story ID | Story Name | Owner | Status
1 | US01 | Correct gender for role | VB | Done
1 | US02 | Divorce before death | SR | Done
1 | US03 | Male last names | ON | Done
1 | US04 | List living single | ON | Done
1 | US05 | Less then 150 years old | VB | Done
1 | US06 | Marriage after 14 | SR | Done
1 | US07 | Siblings should not marry | SR | Done
1 | US08 | Unique IDs | VB | Done
2 | US09 | Fewer than 15 siblings | ON | Done
2 | US10 | Marriage Before Death | SR | Done
2 | US11 | Unique First name Families | SR | Done
2 | US12 | Marriage before Divorced | XP | Done
2 | US13 | Birth before marriage | XP | Done
2 | US14 | Sibling Spacing | VB | Done
2 | US15 | Multiple births <= 5 | VB | Done
2 | US16 | List living married | ON | Done
2 | US17 | Dates before current date | ON | Done
3 | US18 | No marriages to descendants | SR | Coding
3 | US19 | Siblings should not marry | SR | Coding
3 | US20 | First cousins should not marry | XP | Coding
3 | US21 | Aunts and uncles | XP | Coding
3 | US22 | Correct gender for role | VB | Coding
3 | US23 | Unique IDs | VB | Coding
3 | US24 | Unique name and birth date | ON | Coding
3 | US25 | Unique families by spouses | ON | Coding

## Burndown README
The goal of the burndown chart is to help the agile team and customer to understand how the developers are doing
to deliver the product. Burndown charts can be done daily, weekly, at the end of a sprint, or at whatever time interval makes sense.
We'll update our burndown chart for the GEDCOM project at the end of each sprint.
At the end of each sprint, you should update the number of remaining stories, the LOC written to implement the user stories
implemented in this sprint, and the minutes needed to write those lines of code.
Here's a sample burndown chart for a team of three:
Sprint | Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
Start | 2016-06-06 | 24 |  | 0
Sprint 1 | 2016-06-19 | 18 | 6 | 250 | 120 | 125
Sprint 2 | 2016-07-03 | 12 | 6 | 480 | 135 | 102.2222
Sprint 3 | 2016-07-17 | 6 | 6 | 740 | 160 | 97.5
Sprint 4 | 2016-07-31 | 0 | 6 | 1100 | 145 | 148.9655
= # team members * 4 sprints *
2 stories per sprint
lines of code per hour is calcuated by Excel
Velocity of completing user stories (calculated)
Total
LOC
How long to implement the user stories in this sprint
When we expect to complete all user stories

## Burndown
Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
2018-09-18 | 32 |  | 0 | 0
2018-10-06 | 24 | 8 | 317 | 230 | 82.6957
2018-06-16 | 16 | 8 | 365 | 150 | 19.2

## Sprint1
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US01 | Correct gender for role | VB | Done | 15 | 30 | 120 | 90 | Yes
US02 | Divorce before death | SR | Done | 10 | 20 | 20 | 30 | Yes
US03 | Male last names | ON | Done | 20 | 40 | 20 | 40 | Yes
US04 | List living single | ON | Done | 40 | 70 | 20 | 10 | Yes
US05 | Less then 150 years old | VB | Done | 20 | 30 | 10 | 10 | Yes
US06 | Marriage after 14 | XP | Done | 30 | 60 | 15 | 15 | Yes
US07 | Siblings should not marry | SR | Done | 40 | 20 | 10 | 15 | Yes
US08 | Unique IDs | XP | Done | 30 | 30 | 10 | 20 | Yes
Things to do:
Communicate better
Plan ahead of deadlines
Things to avoid:
Not communicating
Starting work on assignments near deadline

## Sprint2
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US09 | Marriage Before Death | SR | Done | 20 | 15 | 30 | 20 | Yes
US10 | Unique First name Families | SR | Done | 40 | 10 | 20 | 10 | Yes
US11 | Marriage before Divorced | VB | Done | 30 | 15 | 30 | 20 | Yes
US12 | Parents not too old | VB | Done | 25 | 25 | 20 | 25 | Yes
US13 | Sibling Spacing | XP | Done | 20 | 15 | 25 | 30 | Yes
US14 | Multiple births <= 5 | XP | Done | 40 | 15 | 30 | 25 | Yes
US15 | List living married | ON | Done | 15 | 10 | 20 | 10 | Yes
US16 | Dates before current date | ON | Done | 15 | 10 | 25 | 15 | Yes
Things to do:
Use Github Better
Learn to use Travis
Things to avoid:
Not using Github

## Sprint3
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US18 | No marriages to descendants | SR | Coding
US19 | Siblings should not marry | SR | Coding
US20 | First cousins should not marry | XP | Coding
US21 | Aunts and uncles | XP | Coding
US22 | Correct gender for role | VB | Coding
US23 | Unique IDs | VB | Coding
US24 | Unique name and birth date | ON | Coding
US25 | Unique families by spouses | ON | Coding

## Sprint4
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed

## Stories
Story ID | Story Name | Story Description
US01 | Dates before current date | Dates (birth, marriage, divorce, death) should not be after the current date
US02 | Birth before marriage | Birth should occur before marriage of an individual
US03 | Birth before death | Birth should occur before death of an individual
US04 | Marriage before divorce | Marriage should occur before divorce of spouses, and divorce can only occur after marriage
US05 | Marriage before death | Marriage should occur before death of either spouse
US06 | Divorce before death | Divorce can only occur before death of both spouses
US07 | Less then 150 years old | Death should be less than 150 years after birth for dead people, and current date should be less than 150 years after birth for all living people
US08 | Birth before marriage of parents | Children should be born after marriage of parents (and not more than 9 months after their divorce)
US09 | Birth before death of parents | Child should be born before death of mother and before 9 months after death of father
US10 | Marriage after 14 | Marriage should be at least 14 years after birth of both spouses (parents must be at least 14 years old)
US11 | No bigamy | Marriage should not occur during marriage to another spouse
US12 | Parents not too old | Mother should be less than 60 years older than her children and father should be less than 80 years older than his children
US13 | Siblings spacing | Birth dates of siblings should be more than 8 months apart or less than 2 days apart (twins may be born one day apart, e.g. 11:59 PM and 12:02 AM the following calendar day)
US14 | Multiple births <= 5 | No more than five siblings should be born at the same time
US15 | Fewer than 15 siblings | There should be fewer than 15 siblings in a family
US16 | Male last names | All male members of a family should have the same last name
US17 | No marriages to descendants | Parents should not marry any of their descendants
US18 | Siblings should not marry | Siblings should not marry one another
US19 | First cousins should not marry | First cousins should not marry one another
US20 | Aunts and uncles | Aunts and uncles should not marry their nieces or nephews
US21 | Correct gender for role | Husband in family should be male and wife in family should be female
US22 | Unique IDs | All individual IDs should be unique and all family IDs should be unique
US23 | Unique name and birth date | No more than one individual with the same name and birth date should appear in a GEDCOM file
US24 | Unique families by spouses | No more than one family with the same spouses by name and the same marriage date should appear in a GEDCOM file
US25 | Unique first names in families | No more than one child with the same name and birth date should appear in a family
US26 | Corresponding entries | All family roles (spouse, child) specified in an individual record should have corresponding entries in the corresponding family records. Likewise, all individual roles (spouse, child) specified in family records should have corresponding entries in the corresponding individual's records. I.e. the information in the individual and family records should be consistent.
US27 | Include individual ages | Include person's current age when listing individuals
US28 | Order siblings by age | List siblings in families by decreasing age, i.e. oldest siblings first
US29 | List deceased | List all deceased individuals in a GEDCOM file
US30 | List living married | List all living married people in a GEDCOM file
US31 | List living single | List all living people over 30 who have never been married in a GEDCOM file
US32 | List multiple births | List all multiple births in a GEDCOM file
US33 | List orphans | List all orphaned children (both parents dead and child < 18 years old) in a GEDCOM file
US34 | List large age differences | List all couples who were married when the older spouse was more than twice as old as the younger spouse
US35 | List recent births | List all people in a GEDCOM file who were born in the last 30 days
US36 | List recent deaths | List all people in a GEDCOM file who died in the last 30 days
US37 | List recent survivors | List all living spouses and descendants of people in a GEDCOM file who died in the last 30 days
US38 | List upcoming birthdays | List all living people in a GEDCOM file whose birthdays occur in the next 30 days
US39 | List upcoming anniversaries | List all living couples in a GEDCOM file whose marriage anniversaries occur in the next 30 days
US40 | Include input line numbers | List line numbers from GEDCOM source file when reporting errors
US41 | Include partial dates | Accept and use dates without days or without days and months
US42 | Reject illegitimate dates | All dates should be legitimate dates for the months specified (e.g., 2/30/2015 is not legitimate)